## Sheet1
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
E1 | Project Setup & Planning | US1 | Initialize project infrastructure | GitHub setup, Database configuration, CI/CD pipeline | Must Have | 8 | To Do | Deekshit gowda HS | Verify repo created | Jathin
E1 | Project Setup & Planning | US2 | Configure development environment | Node.js, npm, Docker, environment variables | Must Have | 5 | To Do | Deekshit gowda HS | Test environment setup | Jathin
E2 | Sprint Planning & Execution | US3 | Create sprint planning module | Sprint backlog UI, Sprint timeline, Duration settings | Should Have | 13 | To Do | Gowtham KC | Test sprint creation | Jathin
E2 | Sprint Planning & Execution | US4 | Implement sprint tracking | Real-time progress updates, Burndown chart | Should Have | 8 | To Do | Gowtham KC | Test burndown chart | Jayaprakash L
E2 | Sprint Planning & Execution | US5 | Sprint review & retrospective | Team feedback form, Sprint metrics | Should Have | 5 | To Do | chetan | Test retrospective form | Jathin
E3 | Team Management | US6 | Add team member assignment | User roles, Permissions, Team hierarchy | Must Have | 5 | To Do | Jayaprakash L | Test role assignment | Gowtham KC
E3 | Team Management | US7 | Create team dashboard | Performance metrics, Team reports, Analytics | Should Have | 8 | To Do | Jayaprakash L | Test dashboard display | Harshith
E4 | Scrum Master Tools | US8 | Standup meeting scheduler | Automated scheduling, Notifications, History | Should Have | 8 | To Do | Jayaprakash L | Test notifications | Harshith
E4 | Scrum Master Tools | US9 | Issue tracking system | Create issues, Link to stories | Could Have | 13 | To Do | Deekshit gowda HS | Test issue creation | Harshith
E5 | Reporting & Analytics | US10 | Generate sprint reports | PDF export, Charts, Metrics summary | Should Have | 8 | To Do | chetan | Test report generation | Deekshit gowda HS
E5 | Reporting & Analytics | US11 | Team performance analytics | Velocity tracking, Productivity metrics | Could Have | 8 | To Do | chetan | Test analytics | chetan