## 1. Product Overview
Item | Description
Product Name | AI Agile Scrum Master
Product Vision/ Purpose | An AI-assisted scrum management platform to automate sprint planning, smart task assignment, daily standups, and sprint analytics.
Business Goals / Key Success factors | Reduce sprint planning effort by 30%, improve on-time completion, increase visibility through real-time reports, and enable reliable GitHub-integrated execution.
Primary Stakeholders | Scrum Master, Product Owner, Development Teams, Engineering Manager, Project Admin

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
| Major features | Mandatory | Mandatory |  |  | (optional) | Mandatory | Mandatory | Mandatory | Mandatory
E1 | Authentication & Organization | US1 | As a user, I want secure sign-up/login and org access so that only authorized members can use the platform. | Registration, login, OTP/email verification, org-member auth middleware | Must Have | 8 | To Do | Backend Team | Auth flow: signup-login-org access | QA Team
|  | US2 | As a user, I want role-based access so that admins and developers see the right features. | Role-based access control for admin/scrum-master/developer | Must Have | 5 | To Do | Backend Team | RBAC permissions validation | QA Team
E2 | Backlog & Sprint Planning | US3 | As a scrum master, I want backlog CRUD so that I can prioritize work. | Backlog item create/update/priority/status APIs + UI | Must Have | 8 | In Progress | Full-stack Team | Backlog CRUD end-to-end | QA Team
|  | US4 | As a scrum master, I want AI-assisted sprint planning so that sprint scope matches capacity. | Capacity calculator + AI recommendations | Must Have | 13 | To Do | AI + Backend | Sprint plan generated from backlog | QA Team
E3 | Task Assignment & Board | US5 | As a lead, I want smart assignment so tasks are balanced by skill and workload. | Skill-gap mapping + assignment scoring | Should Have | 13 | To Do | AI Team | Assignment recommendations accuracy | QA Team
|  | US6 | As a team member, I want a board view so I can move tasks across statuses. | Kanban board with drag-drop and status tracking | Must Have | 8 | In Progress | Frontend Team | Board interactions and status history | QA Team
E4 | Standup, Reports & Monitoring | US7 | As a scrum master, I want standup summaries so blockers are visible daily. | Standup updates capture + AI summary generation | Should Have | 8 | To Do | AI Team | Daily standup summary quality | QA Team
|  | US8 | As a manager, I want sprint reports so I can track velocity and burndown. | Reports API + dashboard charts | Should Have | 5 | To Do | Frontend + Backend | Velocity and burndown report correctness | QA Team
E5 | Integrations | US9 | As a developer, I want GitHub sync so commits/PRs link to sprint tasks. | GitHub webhook + sync service + error handling | Could Have | 8 | Planned | Integrations Team | Webhook ingestion and PR mapping | QA Team
|  | US10 | As admin, I want monitoring alerts so failed automation is quickly detected. | Monitoring dashboard + webhook DLQ panel + alerts | Could Have | 5 | Planned | Platform Team | Failed events visible with retry flow | QA Team
US3
Notes: | MoSCoW
|  | Must Have | Critical requirements that are essential for the project's success and must be delivered.
|  | Should Have | Important requirements that are highly desirable but not vital; the project can still be delivered without them, but it would be less ideal.
|  | Could Have | "Nice-to-have" requirements that are less important and have a lower impact if they are not included.
|  | Won't Have | Requirements that are not being delivered in the current project or timeframe, but may be considered for future iterations.
Story Points
|  | Fibonacci | 0,1,1,2,3,5,8,13,21,34,….
|  | (Modified) | 0,1,1,2,3,5,8,13,20 (points decided based on a User Story's complexity, effort needed & riks)
Ends at 20. Rarely extended to 40 and 100 for very large tasks.

## 3. Roadmap
Release |  | Key Features | Dependencies | Demo Status
Llist Epic Names
v0.1 | 2026-04-20 | Authentication, Org setup, Backlog CRUD | None | On Track
v0.2 | 2026-05-04 | Sprint board, planning assistant | Backlog APIs complete | Planned
v0.3 | 2026-05-18 | AI assignment, standup summaries | AI service integration | Planned
v0.4 | 2026-06-01 | Reports, burndown, velocity | Analytics data pipeline | Planned
v0.5 | 2026-06-15 | GitHub sync and webhooks | GitHub app credentials | Yet to Plan
v1.0 | 2026-06-29 | Monitoring, reliability hardening, MVP release | Pilot onboarding | Yet to Plan
v1.1 | 2026-07-13 | Post-MVP improvements | Pilot feedback | Yet to Plan

## 4. Retrospective
Note: This is for the team to learn and improve. I have taught you in the class on Nov 4, 2025.
Ideally, the team should do this at the end of every release. How often you do , I leave it to you.
What Went Well | What Didn’t Go Well | Improvements / Action Items | Owner
Net time what will you do differently
Backlog and board modules delivered with good collaboration | AI recommendation quality needs more tuning | Add evaluation dataset and weekly model review | AI Lead
Sprint planning meetings became shorter | Webhook failures were detected late | Enable proactive alerts and retry automation | Platform Team